## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Business Move | 50.38 days | July 1, 2024 1:00 PM | September 10, 2024 12:00 PM |  | 1
2 | Yes | Manually Scheduled | Planning the Business Move | 2.5 days | July 1, 2024 1:00 PM | July 3, 2024 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Calculate moving expenses | 1 day | July 1, 2024 1:00 PM | July 2, 2024 12:00 PM |  | 3
4 | Yes | Auto Scheduled | Determine the best method of moving | 4 hrs | July 2, 2024 1:00 PM | July 2, 2024 5:00 PM | 3 | 3
5 | Yes | Auto Scheduled | Create a moving-expense receipt file | 4 hrs | July 3, 2024 8:00 AM | July 3, 2024 12:00 PM | 4 | 3
6 | Yes | Auto Scheduled | Create a moving binder | 4 hrs | July 3, 2024 1:00 PM | July 3, 2024 5:00 PM | 5 | 3
7 | Yes | Auto Scheduled | Finances and Insurance | 4.38 days | July 4, 2024 1:00 PM | July 10, 2024 5:00 PM |  | 2
8 | Yes | Auto Scheduled | Review moving budget | 1 day | July 4, 2024 1:00 PM | July 5, 2024 2:00 PM | 6 | 3
9 | Yes | Auto Scheduled | Verify that belongings are insured for the move | 1 day | July 5, 2024 2:00 PM | July 8, 2024 2:00 PM | 8 | 3
10 | Yes | Auto Scheduled | Appraise valuables specifically insured for the move | 2 days | July 8, 2024 2:00 PM | July 10, 2024 2:00 PM | 9 | 3
11 | Yes | Auto Scheduled | Transfer insurance policies to new address | 3 hrs | July 10, 2024 2:00 PM | July 10, 2024 5:00 PM | 10 | 3
12 | Yes | Auto Scheduled | Select Movers | 10.75 days | July 10, 2024 5:00 PM | July 25, 2024 3:00 PM |  | 2
13 | Yes | Auto Scheduled | Obtain estimates from several moving services | 1 ewk | July 10, 2024 5:00 PM | July 17, 2024 5:00 PM | 11 | 3
14 | Yes | Auto Scheduled | Request references from each moving service | 1 ewk | July 17, 2024 5:00 PM | July 24, 2024 5:00 PM | 13 | 3
15 | Yes | Auto Scheduled | Select moving service | 2 hrs | July 25, 2024 8:00 AM | July 25, 2024 10:00 AM | 14 | 3
16 | Yes | Auto Scheduled | Discuss rough details with movers | 4 hrs | July 25, 2024 10:00 AM | July 25, 2024 3:00 PM | 15 | 3
17 | Yes | Auto Scheduled | Notifications | 1 day | July 25, 2024 3:00 PM | July 26, 2024 3:00 PM |  | 2
18 | Yes | Auto Scheduled | Schedule disconnection of cable and internet at current location | 1 hr | July 25, 2024 3:00 PM | July 25, 2024 4:00 PM | 16 | 3
19 | Yes | Auto Scheduled | Change address with banks and other organization | 2 hrs | July 25, 2024 4:00 PM | July 26, 2024 9:00 AM | 18 | 3
20 | Yes | Auto Scheduled | Send customers notification of move | 4 hrs | July 26, 2024 9:00 AM | July 26, 2024 2:00 PM | 19 | 3
21 | Yes | Auto Scheduled | Set up forwarding of mail | 1 hr | July 26, 2024 2:00 PM | July 26, 2024 3:00 PM | 20 | 3
22 | Yes | Auto Scheduled | New Business Location | 2 days | July 26, 2024 3:00 PM | July 30, 2024 3:00 PM |  | 2
23 | Yes | Auto Scheduled | Order mailing labels, stationary, etc. with new business address | 2 hrs | July 26, 2024 3:00 PM | July 26, 2024 5:00 PM | 21 | 3
24 | Yes | Auto Scheduled | Schedule move with the building management at the new location | 1 day | July 29, 2024 8:00 AM | July 29, 2024 5:00 PM | 23 | 3
25 | Yes | Auto Scheduled | Schedule cable and high-speed Internet installation | 2 hrs | July 30, 2024 8:00 AM | July 30, 2024 10:00 AM | 24 | 3
26 | Yes | Auto Scheduled | Contact utility companies and sign up for new service | 2 hrs | July 30, 2024 10:00 AM | July 30, 2024 12:00 PM | 25 | 3
27 | Yes | Auto Scheduled | Confirm your move date with your moving service | 2 hrs | July 30, 2024 1:00 PM | July 30, 2024 3:00 PM | 26 | 3
28 | Yes | Auto Scheduled | Movers | 0.5 days | July 30, 2024 3:00 PM | July 31, 2024 10:00 AM |  | 2
29 | Yes | Auto Scheduled | Obtain moving service contact numbers | 1 hr | July 30, 2024 3:00 PM | July 30, 2024 4:00 PM | 27 | 3
30 | Yes | Auto Scheduled | Acquire labels for boxes (for example, Fragile, Load First, Load Last) | 1 hr | July 30, 2024 4:00 PM | July 30, 2024 5:00 PM | 29 | 3
31 | Yes | Auto Scheduled | Verify that the moving service has your contact numbers | 1 hr | July 31, 2024 8:00 AM | July 31, 2024 9:00 AM | 30 | 3
32 | Yes | Auto Scheduled | Give moving service written directions to the new location | 1 hr | July 31, 2024 9:00 AM | July 31, 2024 10:00 AM | 31 | 3
33 | Yes | Auto Scheduled | Moving | 4 days | September 4, 2024 1:00 PM | September 10, 2024 12:00 PM |  | 2
34 | Yes | Auto Scheduled | Packing Day | 1 day | September 4, 2024 1:00 PM | September 5, 2024 12:00 PM | 32 | 3
35 | Yes | Auto Scheduled | Moving Day | 1 day | September 6, 2024 4:00 PM | September 9, 2024 4:00 PM | 34 | 3 | Move in must occur on this da only.
36 | Yes | Auto Scheduled | Review all paperwork when the moving service arrives | 1 hr | September 9, 2024 4:00 PM | September 9, 2024 5:00 PM | 35 | 3
37 | Yes | Auto Scheduled | Check carefully for any damaged or missing items | 2 hrs | September 10, 2024 8:00 AM | September 10, 2024 10:00 AM | 36 | 3
38 | Yes | Auto Scheduled | Read and sign bill of lading | 1 hr | September 10, 2024 10:00 AM | September 10, 2024 11:00 AM | 37 | 3
39 | Yes | Auto Scheduled | Retain copies of the bill of lading and inventory | 1 hr | September 10, 2024 11:00 AM | September 10, 2024 12:00 PM | 38 | 3
40 | Yes | Auto Scheduled | Move completed | 0 days | September 10, 2024 12:00 PM | September 10, 2024 12:00 PM | 33 | 2

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Suzane Smith | S | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Vaishnavi Wadhwa | V | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Joseph Schalow | J | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Moving Company | M | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Calculate moving expenses | Suzane Smith | 0 | 8h | 100%
Determine the best method of moving | Suzane Smith | 0 | 4h | 100%
Create a moving-expense receipt file | Suzane Smith | 0 | 4h | 100%
Create a moving binder | Suzane Smith | 0 | 4h | 100%
Review moving budget | Vaishnavi Wadhwa | 0 | 8h | 100%
Verify that belongings are insured for the move | Vaishnavi Wadhwa | 0 | 8h | 100%
Appraise valuables specifically insured for the move | Vaishnavi Wadhwa | 0 | 16h | 100%
Transfer insurance policies to new address | Vaishnavi Wadhwa | 0 | 3h | 100%
Obtain estimates from several moving services | Suzane Smith | 0 | 0h | 100%
Obtain estimates from several moving services | Vaishnavi Wadhwa | 0 | 0h | 100%
Request references from each moving service | Suzane Smith | 0 | 0h | 100%
Request references from each moving service | Vaishnavi Wadhwa | 0 | 0h | 100%
Select moving service | Vaishnavi Wadhwa | 0 | 2h | 100%
Discuss rough details with movers | Vaishnavi Wadhwa | 0 | 4h | 100%
Schedule disconnection of cable and internet at current location | Joseph Schalow | 0 | 1h | 100%
Change address with banks and other organization | Joseph Schalow | 0 | 2h | 100%
Send customers notification of move | Joseph Schalow | 0 | 4h | 100%
Set up forwarding of mail | Joseph Schalow | 0 | 1h | 100%
Order mailing labels, stationary, etc. with new business address | Vaishnavi Wadhwa | 0 | 2h | 100%
Schedule move with the building management at the new location | Vaishnavi Wadhwa | 0 | 8h | 100%
Schedule cable and high-speed Internet installation | Vaishnavi Wadhwa | 0 | 2h | 100%
Contact utility companies and sign up for new service | Vaishnavi Wadhwa | 0 | 2h | 100%
Confirm your move date with your moving service | Vaishnavi Wadhwa | 0 | 2h | 100%
Obtain moving service contact numbers | Joseph Schalow | 0 | 1h | 100%
Acquire labels for boxes (for example, Fragile, Load First, Load Last) | Joseph Schalow | 0 | 1h | 100%
Verify that the moving service has your contact numbers | Joseph Schalow | 0 | 1h | 100%
Give moving service written directions to the new location | Joseph Schalow | 0 | 1h | 100%
Packing Day | Moving Company | 0 | 8h | 100%
Moving Day | Moving Company | 0 | 8h | 100%
Review all paperwork when the moving service arrives | Vaishnavi Wadhwa | 0 | 1h | 100%
Check carefully for any damaged or missing items | Vaishnavi Wadhwa | 0 | 2h | 100%
Read and sign bill of lading | Vaishnavi Wadhwa | 0 | 1h | 100%
Retain copies of the bill of lading and inventory | Vaishnavi Wadhwa | 0 | 1h | 100%